## WholeHouse
Description | Category | Priority | Asset | est. Time | est. Cost Low | est. Cost High | Actual Cost | Completed | Review | Column7
First Floor Windows | Expert | Low |  |  | 1000
Second Floor Windows | Expert | Low |  |  | 1000
Front Door | Expert | Low |  |  | 800
Remove Tile/Linoleum | Demo | High |  |  | 0 | 1000
Install Wood Flooring | Expert/Carpentry | Med |  |  | 1500 | 4000
Install Carpeting | Expert | Low |  |  | 0 | 3000
Replace Plumbing | Plumbing | High |  |  | 300 | 3000
Run Ethernet | Electric | High |  |  | 150
Security System | Electric | Med |  |  | 300 | 600
Trim | Carpentry | Low
Install First Ceiling | Expert | High | Expert
Install Second Ceiling | Expert | High | Expert
Insulate Attic |  | Low | Mike |  | 0 | 500
Extend Back Porch | Carpentry | Very Low |  |  | 300 | 1000 |  |  |  |  | est. Cost Low | est. Cost High
Re-Deck Back Porch |  | Very Low |  |  | 400 | 1000 |  |  |  |  | 6200 | 14750
HVAC Registers |  | Low
HVAC Filter |  | High |  |  | 450 | 650
Area rugs |  | Low
HVAC Thermostat |  | Low
HVAC Compressor |  | Med
Dispose of Tile and Drywall |  | High
Plan and buy Lighting |  | Med
Note on A10: Michael.Stanley: 3/4 vs. 1/2 runs types of valves list of fittings Ground wiring
Note on A14: Kelly: Wiring, Plumbing, Lighting Plan done First!
Note on A15: Kelly: Wiring, Plumbing, Lighting Plan done First!
Note on A16: Kelly: Depends on Ceiling replacement method

## Garage
Description | Category | Asset | Priority | est. Time (hrs) | est. Cost Low | est. Cost High | Actual Cost | Completed | Review | Column7 | Categories
Install Shelving/Bench |  | Mike |  | 6 | 150 | 500 |  |  |  |  | Demo
Organization System | Internet | Mike |  | 4 | 80 | 250
Prep Walls | [10 empty] | Purchase/Find
Paint Walls |  | Family | [8 empty] | Carpentry
Lighting | Electric |  | Low | [7 empty] | Electric
Outlets/Switches | Electric | Mike | Med |  | 50 | 200 |  |  |  |  | Plumbing
Ethernet |  |  | High | [7 empty] | Furniture
Attic Door |  |  | Low |  | 20 | 200 |  |  |  |  | Decision
Exterior Door | Carpentry | Mike/Expert | Med | 4 | 500 | 1500 |  |  |  |  | Paint
Window? |  |  | High
Check for Bugs |  |  | High
Insulate Walls? |  |  | Med
Note on A2: Kelly: Cabinets from Kitchen? Shelves from Costco?
Note on A4: Kelly: After Electric

## TileRoom
Description | Category | Priority | Asset | est. Time (hrs) | est. Cost Low | est. Cost High | Actual Cost | Completed | Review | Column7 |  | Categories
Buy Furniture | Purchase/Find | Low |  |  | 0 | 500 | [5 empty] | Demo
Remove Wood Paneling | Demo | High | Mike | 1.5 | 0 | 0 | [5 empty] | Purchase/Find
Prep Walls for Painting | Demo | High | Contractor |  | 200 | 400 | [5 empty] | Carpentry
Remove Trim | Demo | High |  | 1.5 | 0 | 30 | [5 empty] | Electric
"Build" Closets | Carpentry | Med |  | 3 | 0 | [6 empty] | Plumbing
Replace Sliding Glass Door | Expert | Low |  | 3 | 500 | 1500 | [5 empty] | Furniture
Remove Staples in Subfloor | Demo | High |  | 2 | 0 | 20
Paint Subfloor | Paint | High |  | 1 | 20 | 50 | [5 empty] | Paint | Plain old painting
Paint Walls/Ceiling | Paint | Med |  | 8 | 80 | 200 | [5 empty] | Expert | Specialized
Install Lighting | Electric | High |  | 16 | 250 | 1000
Install Switches/Outlets | Electric | High |  | 16 | 50 | 250
Remove Small Wall | Demo | High |  | 2 | 0 | 20
Replace Garage Door | Expert | Med |  | 3 | 100 | 1000 |  |  |  |  | est. Cost Low | est. Cost High
Clean up room | Demo | High |  | 4 | 0 | 100 |  |  |  |  | 1300 | 5670
Install Trim | Carpentry | Low |  | 8 | 100 | 600
Yank walls with wallpaper? |  | High
Note on A5: Kelly: After Tile is removed
Note on A6: Kelly: Decide what we're going to do with them Remove/Improve/Keep
Note on A7: Kelly: After Ceiling After Tile After woodfloor?
Note on A9: Mike: Before: work below floor After: Painting/Flooring
Note on A16: Kelly: Chair rail Crown Moulding w/corn. Baseboard Doors

## MicroRoom
Description | Category | Priority | Asset | est. Time (hrs) | est. Cost Low | est. Cost High | Actual Cost | Completed | Review | Column7
Remove Wall? | Demo | High |  | 16
Paint Subfloor | Paint | Med
Lighting | Electric | High
Outlets/Switches | Electric | Med
Trim | Carpentry | Low
Redo subfloor | Carpentry | Med
Install rear door?
Note on A5: Kelly: Temporary Kitchen removal
Note on A6: Kelly: Determine Subfloor Health
Note on A8: Kelly: Relocate Switch. Three Way.
Note on A10: Kelly: Mold possibility

## FrontRoom
Description | Category | Priority | Asset | est. Time (hrs) | est. Cost Low | est. Cost High | Actual Cost | Completed | Review | Column7
Remove Wall(s) | Demo | High
Trim | Carpentry | Low
Door to MicroRoom? |  | Low |  |  | 100 | 600
Note on A6: Kelly: Hall Wall. Widen micro room doorway?

## Kitchen
Description | Category | Priority | Asset | est. Time (hrs) | est. Cost Low | est. Cost High | Actual Cost | Completed | Review | Column7
Remove Wallpaper | Demo | High
Remove Trim | Demo | High
Remove Wall Tile | Demo | High
Remove Cabinets | Demo | Med
Remove mini wall? | Demo | Med
Prep Plumbing | Plumbing | Med
Prep Electric | Electric | High
Remove Pantry? | Demo | Med |  | 2 | 0 | 50

## Outside
Description | Category | Priority | Asset | est. Time (hrs) | est. Cost Low | est. Cost High | Actual Cost | Completed | Review | Column7
Ground wiring | Electrical
Shutters
Soffit
Pressure wash siding
ground cover under deck
remove tree

## Tools
Tools | Materials
Paint Sprayer | Yard seed/killer/fertilizer
Air compressor | Plywood (Subfloor)
Nailgun
Short Ladder
Roof ladder
Seed spreader
Miter Saw (trim)
Hedge Trimmer
Harwood flooring nailer