## WholeHouse
Description | Category | Column1 | Asset | est. Time | est. Cost Low | est. Cost High | Actual Cost | Completed | Review | Column7
First Floor Windows | Expert |  |  |  | 1000
Second Floor Windows | Expert |  |  |  | 1000
Front Door | Expert |  |  |  | 800
Remove Tile/Linoleum | Demo |  |  |  | 0 | 1000
Install Wood Flooring | Expert/Carpentry |  |  |  | 1500 | 4000
Install Carpeting | Expert |  |  |  | 250 | 3000
Replace Plumbing | Plumbing |  |  |  | 300 | 3000
Run Ethernet | Electric
Security System | Electric |  |  |  | 300 | 600
Trim | Carpentry
Remove First Ceiling | Demo |  |  |  | 100
Remove Second Ceiling | Demo |  |  |  | 100
Install First Ceiling | Expert
Install Second Ceiling
Insulate Attik |  |  |  |  | 0 | 500
Extend Back Porch |  |  |  |  | 300 | 1000 |  |  |  |  | est. Cost Low | est. Cost High
Re-Deck Back Porch |  |  |  |  | 400 | 1000 |  |  |  |  | 6500 | 14750
HVAC Registers
HVAC Filter |  |  |  |  | 450 | 650
Area rugs
HVAC Thermostat
Note on A16: Kelly: Wiring, Plumbing, Lighting Plan done First!
Note on A17: Kelly: Wiring, Plumbing, Lighting Plan done First!
Note on A18: Kelly: Depends on Ceiling replacement method

## Garage
Description | Category | Column1 | Asset | est. Time (hrs) | est. Cost Low | est. Cost High | Actual Cost | Completed | Review | Column7 | Categories
Install Shelving/Bench |  |  | Mike | 6 | 150 | 500 |  |  |  |  | Demo
Organization System |  |  | Mike | 4 | 80 | 250
Prep Walls | [10 empty] | Purchase/Find
Paint Walls |  |  | Family | [7 empty] | Carpentry
Lighting | Electric | [9 empty] | Electric
Outlets/Switches |  |  |  |  | 50 | 200 |  |  |  |  | Plumbing
Ethernet | [10 empty] | Furniture
Attik Door |  |  |  |  | 20 | 200 |  |  |  |  | Decision
Exterior Door | Carpentry |  | Mike/Expert | 4 | 500 | 1500 |  |  |  |  | Paint
Window?
Check for Bugs
Insulate Walls
Note on A2: Kelly: Cabinets from Kitchen? Shelves from Costco?
Note on A4: Kelly: After Electric

## TileRoom
Description | Category | Column1 | Asset | est. Time (hrs) | est. Cost Low | est. Cost High | Actual Cost | Completed | Review | Column7 |  | Categories
Remove Wallpaper | Demo |  |  |  | 0 | 500 | [5 empty] | Demo
Remove Wood Paneling | Demo |  | Mike | 1.5 | 0 | 0 | [5 empty] | Purchase/Find
Prep Walls for Painting | Demo |  | Contractor |  | 200 | 400 | [5 empty] | Carpentry
Remove Trim | Demo |  |  | 1.5 | 0 | 30 | [5 empty] | Electric
"Build" Closets | Carpentry |  |  | 3 | 0 | [6 empty] | Plumbing
Replace Sliding Glass Door | Expert |  |  | 3 | 500 | 1500 | [5 empty] | Furniture
Remove Staples in Subfloor | Demo |  |  | 2 | 0 | 20
Paint Subfloor | Paint |  |  | 1 | 20 | 50 | [5 empty] | Paint | Plain old painting
Paint Walls/Ceiling | Paint |  |  | 8 | 80 | 200 | [5 empty] | Expert | Specialized
Install Lighting | Electric |  |  | 16 | 250 | 1000
Install Switches/Outlets | Electric |  |  | 16 | 50 | 250
Remove Small Wall | Demo |  |  | 2 | 0 | 20
Buy Furniture | Purchase/Find |  |  |  | 0 | 1000
Replace Garage Door | Expert |  |  | 3 | 100 | 1000 |  |  |  |  | est. Cost Low | est. Cost High
Clean up room | Demo |  |  | 4 | 0 | 100 |  |  |  |  | 1400 | 6670
Install Trim | Carpentry |  |  | 8 | 200 | 600
Note on A5: Kelly: After Tile is removed
Note on A6: Kelly: Decide what we're going to do with them Remove/Improve/Keep
Note on A7: Kelly: After Ceiling After Tile After woodfloor?
Note on A9: Mike: Before: work below floor After: Painting/Flooring
Note on A17: Kelly: Chair rail Crown Moulding w/corn. Baseboard Doors

## MicroRoom
Description | Category | Column1 | Asset | est. Time (hrs) | est. Cost Low | est. Cost High | Actual Cost | Completed | Review | Column7
Remove Wall | Demo |  |  | 16
Paint Subfloor | Paint
Lighting
Outlets/Switches | Electric
Trim | Carpentry
Redo subfloor
Note on A5: Kelly: Temporary Kitchen removal
Note on A6: Kelly: Determine Subfloor Health
Note on A8: Kelly: Relocate Switch. Three Way.
Note on A10: Kelly: Mold possibility

## FrontRoom
Description | Category | Column1 | Asset | est. Time (hrs) | est. Cost Low | est. Cost High | Actual Cost | Completed | Review | Column7
Remove Wall(s) | Demo
Trim | Carpentry
Door to MicroRoom? |  |  |  |  | 100 | 600
Note on A6: Kelly: Hall Wall. Widen micro room doorway?

## Kitchen
Description | Category | Column1 | Asset | est. Time (hrs) | est. Cost Low | est. Cost High | Actual Cost | Completed | Review | Column7
Remove Wallpaper
Remove Trim
Remove Wall Tile
Remove Cabinets
Remove mini wall?
Prep Plumbing
Prep Electric
Remove Pantry? |  |  |  | 2 | 0 | 50

## Sheet8
Description | Category | Column1 | Asset | est. Time (hrs) | est. Cost Low | est. Cost High | Actual Cost | Completed | Review | Column7

## Tools
Tools | Materials
Paint Sprayer | 1" screws
Air compressor | 3" Screws
Nailgun | plywood (shelves)
Short Ladder | 2x4 (shelves)
Roof ladder | Yard seed/killer/fertilizer
Seed spreader | Plywood (Subfloor)
Miter Saw (trim)
Hedge Trimmer